## Tasks
task_id | description | optimistic_time | most_likely_time | pessimistic_time | dependencies
T1 | Requirement Gathering | 3 | 5 | 10
T2 | Design Phase | 4 | 6 | 12 | T1
T3 | Development - Module A | 5 | 8 | 15 | T2
T4 | Development - Module B | 6 | 9 | 18 | T2
T5 | Integration | 2 | 3 | 5 | T3,T4
T6 | Testing | 3 | 5 | 8 | T5
T7 | Documentation | 1 | 2 | 3 | T2
T8 | Deployment | 1 | 1 | 2 | T6,T7